FWO-MOB-001  ·  Rev.0  ·  26 August 2026

Fatimah Work OS

Mobile Application Programme

Architecture, Phase Plan and Engineering Handover

From single-file web app to store-published mobile application

| Field | Value |
| --- | --- |
| Document ID | FWO-MOB-001 |
| Revision | Rev.0 — issued for execution |
| Product | Fatimah Work OS (fatimah-work-os.vercel.app) |
| Source of truth | github.com/farajaay/fatimah-work-os (private, branch main) |
| Backend | Supabase — existing project, contract unchanged |
| Objective | Publish an installable mobile application on Apple App Store and Google Play |
| Intended executor | Claude Code or ChatGPT Codex, driven ticket-by-ticket |
| Companion files | MOBILE_BUILD_PLAN.md (agent brief) · CLAUDE.md (guardrails) · 2 architecture diagrams |
| Hard boundary | No ATEMA data, infrastructure or credentials enter this programme |

# Contents

If the list below appears empty, open in Word and press Ctrl+A then F9 to build the field.

# 1.  Executive Summary

Fatimah Work OS today is a single 30 KB index.html file: inline CSS, inline JavaScript, an Arabic right-to-left interface, five product views, and a direct browser connection to Supabase using a publishable client key with Row Level Security as the security boundary. It is deployed as a static site on Vercel with no build step. As a web product it works. As a candidate for the App Store and Google Play, it has four structural gaps and one strategic question.

### The four structural gaps

- No build output. Native shells package a folder of compiled assets. There is nothing to package until a bundler is introduced.

- A runtime CDN dependency. The Supabase client is fetched from jsDelivr at load. A shipped binary that cannot start without a third-party CDN is fragile and is a legitimate review concern. It must be bundled.

- No offline behaviour and no application manifest. A mobile app that shows a blank screen in a lift is not a mobile app.

- A desktop-first layout. The sidebar grid and pointer-sized targets do not survive contact with a 390-point phone screen, and the session is held in browser storage that iOS may evict.

### The strategic question

A pure Progressive Web App cannot be listed on the Apple App Store — Apple accepts only signed native binaries. The route to both stores is therefore a Capacitor native shell wrapping the existing web application. Capacitor is chosen deliberately: it preserves the interface exactly as designed, requires no rewrite in React Native or Flutter, and produces genuine Xcode and Gradle projects that satisfy both stores.

But a web view wrapped in a native binary and nothing more is rejected under App Store Review Guideline 4.2 (minimum functionality). The programme therefore treats native capability as a required phase, not a nice-to-have: push notifications for follow-ups, camera capture for task evidence, a biometric app lock, native share, and secure session storage. Each of these also happens to make the product materially better on a phone, which is the point.

### Recommended shape

| Track | Recommendation |
| --- | --- |
| Immediate value | Ship the installable PWA first (Phases 0–3, roughly two weeks). It is usable on the home screen on both platforms, needs no store review, and de-risks everything downstream. |
| Google Play | Capacitor Android build. Straightforward. Budget for the 12-tester / 14-day closed test that personal developer accounts must complete before production release. |
| Apple App Store | Capacitor iOS build. Requires a Mac or a macOS CI runner, an Apple Developer Program membership, and Phases 6 and 7 completed in full before the first submission. |
| Audience decision | Resolve in Phase 0. If the app remains for one named user, TestFlight distribution is the correct and lower-friction answer; public listing of a single-user app invites rejection. |

Estimated effort: 25–30 focused working days, roughly eight calendar weeks including store review. Recurring cost is 99 USD per year (Apple) plus a one-time 25 USD (Google).

# 2.  Baseline Assessment

Established by direct inspection of the supplied repository snapshot. This is the factual starting position; every phase below is written against it.

| Attribute | Current state | Implication for the programme |
| --- | --- | --- |
| Frontend | One file, index.html, 30,175 bytes. CSS and JavaScript inline. | No artefact for a native shell to package. Phase 1 is mandatory and first. |
| Framework | None — vanilla DOM manipulation. lang="ar", dir="rtl". | Keep it. A React or Flutter rewrite adds risk and cost for no store benefit. |
| Dependency | @supabase/supabase-js@2 loaded from cdn.jsdelivr.net at runtime. | Must become a bundled npm dependency. A native binary must not require a CDN to boot. |
| Configuration | Supabase project URL and publishable key hardcoded in the file. | Move to build-time environment variables. Note that a key inside a shipped binary cannot be rotated without a new release. |
| Data model | 11 relations in use: tasks, achievements, design_concepts, events, task_evidence, workflow_runs, workflow_run_steps, workflow_steps, workspace_members, v_control_exceptions, v_project_progress. | This is a stable contract. It does not change during this programme. |
| Views | Five: Today, Projects, Workflow, Event Radar, Career. | Maps cleanly onto five bottom tabs. No information architecture work required. |
| Authentication | Supabase Auth, email and password only. No social sign-in. | Sign in with Apple is therefore not triggered. One less obligation. |
| Offline | None. Every view requires a live network call. | Blocking for a credible mobile product. Phase 4. |
| PWA assets | No manifest, no service worker, no icons, no splash. | Phase 2. |
| Layout | CSS grid with a fixed sidebar; desktop-first. viewport-fit=cover already present. | Phase 3. The visual language and colour tokens are good and are preserved. |
| Session storage | Supabase default — browser localStorage. | iOS WKWebView may evict this, silently logging the user out. Must move to native secure storage. |
| Hosting | Vercel static, cleanUrls, no build command. | Keep the project and domain. Add a build step. |
| Realtime | No channel subscriptions in the client, although the schema supports it. | Optional enhancement in Phase 4. |
| Migrations | Six migrations already applied to production. | Documented, not re-run. Only additive migrations are permitted, and only in Phase 7. |

# 3.  Decision D-1 — Distribution Route

Four routes were considered. The comparison below is what justifies the architecture in Section 5.

| Route | Apple Store | Google Play | Effort | Assessment |
| --- | --- | --- | --- | --- |
| A. Installable PWA only | Not possible | Not possible | Small | Excellent product, zero store presence. Correct as an interim step, not as the destination. |
| B. Play TWA + PWA on iOS | Not possible | Yes | Medium | Gets one store cheaply. Leaves iOS — the more likely device — without a store listing. Half a solution. |
| C. Capacitor, both platforms | Yes | Yes | Large | RECOMMENDED. Keeps the existing codebase intact, produces real Xcode and Gradle projects, gives access to native APIs that satisfy Guideline 4.2 and genuinely improve the product. |
| D. React Native or Flutter rewrite | Yes | Yes | Very large | Discards a working, well-designed application and rebuilds it. Not justified by any requirement in this programme. |

### Decision

Route C, executed in two waves: the PWA layer ships first and stands on its own (Phases 0–4), then the Capacitor shells wrap that same artefact (Phases 5–9). One codebase, one build, three distribution targets. Nothing is thrown away at any point.

# 4.  Store Gate Risks

These are the failure modes that actually cause rejection. Each is assigned to the phase that closes it. Read this table before writing any code.

| ID | Risk | Mitigation | Closed in |
| --- | --- | --- | --- |
| R-1 | Apple Guideline 4.2 — minimum functionality. A wrapped website with no native capability is refused. | Ship push notifications, camera evidence capture, biometric lock, native share and haptics. Demonstrate them in the review notes and the screenshots. | Phase 6 |
| R-2 | Apple Guideline 5.1.1(v) — an app that lets a user create an account must let them delete it inside the app. | Settings screen with account deletion, backed by a Supabase Edge Function using the service role. Include a data export alongside it. | Phase 7 |
| R-3 | Audience. An application serving one named individual is not a public App Store product. | Decide in Phase 0: TestFlight-only (recommended if it stays personal), Apple Business Manager custom app, or generalise into a multi-user product. | Phase 0 |
| R-4 | Google Play — personal developer accounts must run a closed test with 12 testers for 14 continuous days before production access. | Start the closed track the moment the first Android build is stable. It runs in parallel with iOS work; it is calendar time, not effort. | Phase 9 |
| R-5 | The app is entirely behind a login. Reviewers who cannot get in reject on sight. | Create a dedicated demo account with seeded, non-personal data. Supply credentials in App Review notes and Play testing instructions. | Phase 7 |
| R-6 | Missing iOS permission usage strings cause an immediate binary rejection. | NSCameraUsageDescription, NSPhotoLibraryUsageDescription, NSFaceIDUsageDescription written in Arabic and English, each explaining the actual purpose. | Phase 6 |
| R-7 | The Supabase publishable key is embedded in a shipped binary and cannot be rotated without a release. | Accept the residual risk — RLS is the real boundary — but confirm no table is readable without an authenticated JWT, and keep a documented rotation-plus-release runbook. | Phase 7 |
| R-8 | Requiring push notifications for core functionality is not permitted by Apple. | Push is an enhancement. Every feature must remain fully usable with notifications denied. | Phase 6 |
| R-9 | Play Data Safety declaration inconsistent with actual SDK behaviour is a policy violation. | Complete the form from a written inventory of every field transmitted, generated in Phase 7 — not from memory. | Phase 7 |
| R-10 | Arabic-only interface with English store metadata confuses reviewers. | Arabic primary listing plus an English listing. Screenshots in Arabic. Review notes in English. | Phase 9 |

Arabic-language user interface strings are a product strength, not a risk — both stores fully support Arabic localisation and right-to-left layouts.

# 5.  Target Architecture

Six layers. Read from the bottom: the backend contract is fixed and untouched; everything above it is what this programme builds. Figure 1 overleaf shows the target stack; Figure 2 shows how the ten phases gate into the release pipeline.

## 5.1  Figures

Figure 1 — Target architecture (overleaf, landscape).

Figure 2 — Execution workflow and release pipeline (overleaf, landscape).

Figure 1 — Target architecture. Layers 3 to 5 are new work; Layer 6 is the existing Supabase project and does not change.

Figure 2 — Phase gates and the build/release pipeline. One build artefact feeds three distribution targets.

## 5.2  Layer responsibilities

| Layer | Responsibility and design rules |
| --- | --- |
| 1 — Distribution | Four channels from one artefact: App Store (or TestFlight), Google Play, the installable PWA on Vercel, and optionally an Apple Business Manager custom app. The web channel ships continuously; the store channels ship on a release cadence. |
| 2 — Native shell | Capacitor. iOS runs in WKWebView, Android in the system WebView. The shell owns nothing but the bridge: it exposes native APIs to the web layer and never contains business logic. If a feature works only in the shell, the architecture has been violated. |
| 3 — PWA / offline | Manifest, service worker, precached shell, an IndexedDB read cache and a write outbox. This layer is what makes the app open instantly and survive a dead network — on the web and inside the native shell equally. |
| 4 — Application core | Vite plus TypeScript over the existing vanilla DOM code. The five feature modules keep their current behaviour and appearance. New: a router with a mobile bottom-tab shell, a typed state store, extracted CSS tokens, a platform adapter, and telemetry. |
| 5 — Data access | Supabase client bundled, not fetched. One typed repository per table; feature modules never call the client directly. A custom auth storage adapter writes the session to native secure storage. Realtime subscriptions carry reconnection and backoff. |
| 6 — Backend | The existing Supabase project. Auth, Postgres with RLS, Storage for evidence photos. The only additions permitted are three Edge Functions: push dispatch, account deletion, and data export — all additive, none altering existing tables or policies. |

## 5.3  The platform adapter — the rule that keeps this maintainable

One code path serves both runtimes. Feature code asks the adapter for a capability and gets either the native implementation or a web fallback. It never branches on platform.

// src/platform/capabilities.ts

import { Capacitor } from '@capacitor/core';

export const isNative = () => Capacitor.isNativePlatform();

export const platform = () => Capacitor.getPlatform(); // 'ios' | 'android' | 'web'

// Correct: the caller does not know or care which runtime it is in.

export async function captureEvidence(): Promise<Blob | null> {

return isNative() ? nativeCamera() : fileInputFallback();

}

// Wrong: never do this inside a feature module.

// if (Capacitor.getPlatform() === 'ios') { ...duplicate the whole view... }

# 6.  Target Repository Structure

The agent creates this structure in Phase 1. The existing index.html is decomposed into it — not deleted and not rewritten from scratch.

fatimah-work-os/

├─ .github/workflows/

│   ├─ ci.yml                 lint · typecheck · unit · e2e · build

│   ├─ release-android.yml    build .aab, upload to Play internal track

│   └─ release-ios.yml        macOS runner, build .ipa, upload to TestFlight

├─ android/                   generated by Capacitor — committed

├─ ios/                       generated by Capacitor — committed

├─ public/

│   ├─ icons/                 192/512 + maskable + iOS 1024

│   └─ manifest.webmanifest

├─ src/

│   ├─ main.ts                bootstrap, session restore, route to auth or shell

│   ├─ app/

│   │   ├─ router.ts          hash router, five routes

│   │   ├─ shell.ts           bottom tabs (mobile) / sidebar (>= 900px)

│   │   ├─ state.ts           typed store, optimistic mutations

│   │   └─ types.ts           generated Supabase row types

│   ├─ features/

│   │   ├─ today/  projects/  workflow/  events/  career/

│   │   ├─ auth/             login, signup, biometric unlock

│   │   └─ settings/         account deletion, data export, notifications

│   ├─ data/

│   │   ├─ supabase.ts       client factory + env config

│   │   ├─ session-storage.ts custom auth storage adapter (native secure)

│   │   ├─ repositories/     one file per table, typed

│   │   ├─ cache.ts          IndexedDB read cache

│   │   └─ outbox.ts         offline write queue + replay

│   ├─ platform/

│   │   ├─ capabilities.ts  push.ts  camera.ts  biometric.ts  share.ts  haptics.ts

│   ├─ styles/

│   │   ├─ tokens.css        extracted verbatim from index.html :root

│   │   ├─ base.css  layout.css  components.css  safe-area.css

│   └─ sw/ custom-sw.ts      Workbox routing

├─ supabase/functions/

│   ├─ delete-account/  dispatch-push/  export-data/

├─ tests/

│   ├─ e2e/                  Playwright: auth, five views, offline, outbox

│   └─ unit/                 Vitest: outbox, cache, repositories

├─ capacitor.config.ts

├─ vite.config.ts

├─ .env.example              VITE_SUPABASE_URL, VITE_SUPABASE_ANON_KEY

├─ CLAUDE.md                 agent guardrails — read first, every session

├─ MOBILE_BUILD_PLAN.md      ticket backlog

└─ package.json

# 7.  Technology Stack

| Concern | Choice | Reason |
| --- | --- | --- |
| Bundler | Vite 5+ | Fastest path from a static file to a build output. Native ESM, trivial config, first-class PWA plugin. |
| Language | TypeScript, strict | The current file has no types and eleven relations flowing through it. Types are the cheapest defect prevention available here. |
| UI framework | None — keep vanilla DOM | The interface is already built and looks the way it should. Introducing a framework is pure risk. |
| PWA | vite-plugin-pwa (Workbox) | Generates manifest and service worker, handles precache manifests and update prompts. |
| Native shell | Capacitor 7 | Real Xcode and Gradle projects, a mature plugin ecosystem, and no rewrite. |
| Native plugins | @capacitor/app, browser, camera, device, haptics, keyboard, network, preferences, push-notifications, share, splash-screen, status-bar; capacitor-native-biometric | The set that closes Guideline 4.2 and delivers real mobile value. |
| Local storage | idb (IndexedDB wrapper) | Read cache and outbox. Survives WebView memory pressure better than localStorage. |
| Testing | Vitest (unit) + Playwright (E2E) | Playwright can drive the web build; the same specs guard against regressions in the shell. |
| Monitoring | @sentry/browser + Capacitor integration | Store-published apps cannot be debugged by looking over a shoulder. Crash and performance telemetry, no personal data. |
| CI/CD | GitHub Actions + Fastlane | Ubuntu runner for web and Android; macOS runner for iOS. Fastlane handles signing and upload. |
| Quality | ESLint + Prettier + tsc --noEmit | Enforced in CI, not by discipline. |

# 8.  Phase Plan

Ten phases. Each has an objective, a scope, and an exit gate. A phase is not finished until its gate passes — the gate is what the agent is measured against, not the number of files it touched.

## Phase 0  ·  Baseline and Guardrails

Objective: Freeze a known-good reference, resolve the audience question, and establish the rules the agent will work under.

Scope

- Tag the current production commit as v0-web-baseline. This is the rollback point and the visual reference.

- Create branch feat/mobile-app. All work lands there until Phase 4 passes.

- Write CLAUDE.md with the guardrails in Appendix C. Every agent session begins by reading it.

- Capture reference screenshots of all five views at 390px, 768px and 1440px widths, in Arabic RTL. These are the pixel-parity baseline for Phase 1.

- Secret audit: confirm no service-role key, database password or corporate document exists anywhere in git history.

- DECISION REQUIRED — audience (Risk R-3): public listing, TestFlight-only, or Apple Business Manager custom app. Everything in Phases 7 and 9 depends on this answer.

Exit gate: Baseline tag exists, branch created, CLAUDE.md committed, screenshots stored under docs/baseline/, audience decision recorded in the document control table.

Estimated effort: 1 day

## Phase 1  ·  Modularisation — Vite and TypeScript

Objective: Convert one file into a buildable, typed project with zero visible change. This is the highest-risk phase precisely because nothing should appear to happen.

Scope

- Scaffold Vite with TypeScript. Move index.html to the project root as the entry template.

- Extract the :root CSS custom properties verbatim into src/styles/tokens.css. Do not adjust a single colour value.

- Split the remaining CSS into base, layout and components files. No rule changes.

- Split the JavaScript into src/app/ and src/features/. Preserve function behaviour exactly; only module boundaries change.

- Replace the jsDelivr script tag with npm @supabase/supabase-js. Move URL and key to VITE_ prefixed environment variables; commit .env.example, never .env.

- Generate row types from the live schema (supabase gen types typescript) into src/app/types.ts.

- Introduce one typed repository per table under src/data/repositories/. Feature modules stop calling supabase.from() directly.

- Configure Vercel: build command npm run build, output directory dist. Domain and Supabase project unchanged.

Exit gate: npm run build succeeds; tsc --noEmit is clean; the deployed preview is pixel-identical to the Phase 0 screenshots at all three widths; login, task creation, task completion and all five views behave exactly as before.

Estimated effort: 3–4 days

## Phase 2  ·  PWA Layer

Objective: Make the web application installable and give it an offline shell.

Scope

- Add vite-plugin-pwa. Manifest: name, Arabic short_name, dir "rtl", lang "ar", display "standalone", background and theme colours from the existing tokens.

- Produce the icon set — 192, 512, maskable 512, Apple touch 180, App Store 1024 — from the "F" monogram already in the design.

- iOS meta tags: apple-mobile-web-app-capable, status bar style, and generated splash images.

- Workbox strategy: precache the application shell; network-first for Supabase REST calls with a cached fallback; stale-while-revalidate for static assets.

- Implement an update flow: when a new service worker is waiting, show a discreet Arabic "تحديث متاح" prompt rather than reloading underneath the user.

Exit gate: Lighthouse PWA category passes; the app installs to the home screen on iOS Safari and Android Chrome; with the network disabled it opens to a designed offline state rather than a browser error page.

Estimated effort: 2 days

## Phase 3  ·  Mobile User Experience

Objective: Make the interface belong on a phone without abandoning the desktop layout.

Scope

- Responsive shell: bottom tab bar with the five existing views below 900px; the current sidebar at and above it. One router, two presentations.

- Safe-area insets on every fixed element using env(safe-area-inset-*). viewport-fit=cover is already set.

- Raise every interactive target to a minimum of 44 by 44 points. Several current buttons are below this.

- Verify RTL under the new layout: tab order, swipe direction, icon mirroring, and any latin-script inputs that must stay LTR.

- Replace blocking spinners with skeleton states so a slow network reads as loading, not as broken.

- Prevent the iOS keyboard from displacing fixed elements; keep inputs at 16px to stop automatic zoom.

- Add pull-to-refresh on the Today and Projects views.

Exit gate: All five views usable one-handed on a 390pt viewport; no horizontal scrolling; no element under the notch or home indicator; RTL correct throughout; verified on a real iPhone and a real Android device.

Estimated effort: 3–4 days

## Phase 4  ·  Offline and Synchronisation

Objective: Let the application be useful when the network is not.

Scope

- IndexedDB read cache. Every view renders last-known data immediately, then refreshes and reconciles.

- Write outbox: mutations are queued with an idempotency key, applied optimistically to the interface, and replayed when connectivity returns.

- Reconnection: listen to Capacitor Network status on native and the online event on web; replay with exponential backoff.

- Conflict policy — last write wins on updated_at, with one exception: task completion is monotonic. A completed task does not revert because a stale write arrived late.

- Never queue authentication operations or evidence file deletions; both must fail loudly and immediately.

- Surface a pending-sync count in the header so the user always knows what has not yet reached the server.

- Optional: Supabase Realtime subscriptions on tasks and events, with backoff.

Exit gate: Aeroplane-mode test passes end to end — open the app, read all five views from cache, create and complete tasks, restore connectivity, and confirm every queued change lands exactly once with no duplicates.

Estimated effort: 4–5 days

## Phase 5  ·  Capacitor Native Shells

Objective: Produce real iOS and Android projects around the existing build output.

Scope

- npm install @capacitor/core @capacitor/cli; npx cap init with appId com.farajaay.fatimahworkos and appName "Fatimah Work OS".

- capacitor.config.ts: webDir "dist", androidScheme "https", splash and status bar configured to the brand palette.

- npx cap add ios; npx cap add android. Commit both native projects.

- Icons and splash screens via @capacitor/assets from a single 1024px source.

- Status bar and splash plugins; edge-to-edge display on Android.

- Hardware back button on Android: navigate back through the router, and exit only from a root tab.

- Deep links — Universal Links on iOS and App Links on Android — for authentication callbacks and direct task URLs.

- Lock down navigation: no allowNavigation entries to arbitrary domains; external links open in the system browser via @capacitor/browser.

Exit gate: Both projects build and run on a physical device; the application looks and behaves as it does on the web; the back button behaves correctly; deep links resolve.

Estimated effort: 2–3 days

## Phase 6  ·  Native Capabilities  (closes Risk R-1)

Objective: Add the native functionality that makes this an application rather than a wrapped page. This phase is what stands between the build and an Apple approval.

Scope

- Secure session storage: a custom Supabase auth storage adapter backed by @capacitor/preferences, which uses the iOS Keychain and Android EncryptedSharedPreferences. This also fixes the silent-logout problem inherited from localStorage.

- Biometric app lock (Face ID / Touch ID / Android BiometricPrompt) with a configurable grace period and a passcode fallback. Optional for the user, off by default.

- Push notifications: APNs and FCM registration, token persisted per device, dispatched from a Supabase Edge Function on task due dates and event radar changes. Everything remains fully usable if permission is denied.

- Camera capture for task evidence, writing to Supabase Storage against the existing task_evidence relation. On the web the same call falls back to a file input.

- Native share sheet for tasks, events and career achievements.

- Haptic feedback on task completion and pull-to-refresh — small, but it is the difference between feeling native and feeling embedded.

- iOS permission usage strings in Info.plist, written in Arabic and English, each stating the real purpose.

- Android runtime permission requests with in-context rationale, never on first launch.

Exit gate: Every capability demonstrable on a physical device; the application remains fully functional with all permissions denied; permission strings present and accurate; a short screen recording is captured for the App Review notes.

Estimated effort: 4–5 days

## Phase 7  ·  Store Compliance and Account Lifecycle

Objective: Close the legal and policy gates. These are binary — they either exist or the submission fails.

Scope

- Account deletion inside the application (Risk R-2): a Settings entry, a clear consequence warning, a confirmation step, then a Supabase Edge Function using the service role that removes the auth user and all owned rows.

- Data export: a JSON download of everything the user owns, offered next to deletion.

- Privacy policy and terms of service, published at stable public URLs and linked from both the Settings screen and the store listings.

- Build a written field-level inventory of every item transmitted to Supabase, Sentry and the push services. Complete the Play Data Safety form and the App Store Privacy nutrition label from that inventory (Risk R-9).

- Create and seed a reviewer demo account containing plausible, entirely non-personal data (Risk R-5).

- Confirm no relation is readable without an authenticated JWT — a direct anonymous REST call against every table must return zero rows (Risk R-7).

- Age rating questionnaires, export-compliance declaration, and the content-rights attestation.

Exit gate: Deletion works end to end and is irreversible; export produces valid JSON; policy URLs resolve publicly; demo account tested from a clean device; anonymous access confirmed impossible on all eleven relations.

Estimated effort: 3 days

## Phase 8  ·  Quality Gates

Objective: Prove the thing works before anyone outside sees it.

Scope

- Playwright end-to-end suite: authentication, all five views, task lifecycle, offline behaviour, outbox replay, account deletion.

- Vitest unit coverage on the outbox, the cache and the repositories — the components where a silent bug loses data.

- Lighthouse thresholds enforced in CI: Performance 90+, Accessibility 95+, Best Practices 95+, PWA passing.

- Device matrix: iPhone SE (small), iPhone 15 Pro (notch and Dynamic Island), a mid-range Android, and a tablet. Cold start under three seconds on the slowest.

- Accessibility: contrast against the existing palette, VoiceOver and TalkBack navigation in Arabic, dynamic type at 200 percent without clipping.

- Sentry wired with release tagging and source maps uploaded from CI.

Exit gate: CI green on every gate; the device matrix signed off with evidence; no critical or high accessibility findings outstanding.

Estimated effort: 2–3 days

## Phase 9  ·  Release Engineering and Submission

Objective: Ship it, and make shipping it again boring.

Scope

- Semantic versioning with a single source of truth feeding package.json, Info.plist and build.gradle.

- GitHub Actions: ci.yml on every pull request; release-android.yml producing a signed .aab to the Play internal track; release-ios.yml on a macOS runner producing an .ipa to TestFlight.

- Signing: Android keystore and Apple certificates stored as encrypted repository secrets. The keystore is also backed up offline — losing it means losing the ability to update the app, permanently.

- Store assets: Arabic and English listings, screenshots from the device matrix, feature graphic, and English review notes describing the native capabilities and supplying the demo credentials.

- Google Play: internal track, then the closed test with 12 testers for 14 days (Risk R-4), then a staged production rollout at 10 → 50 → 100 percent.

- Apple: TestFlight internal, then external if applicable, then submission. Expect one rejection round; budget for it rather than being surprised by it.

- Publish a rollback runbook — Play staged-rollout halt, and an expedited-review path for iOS.

Exit gate: A tagged release builds unattended and lands in both TestFlight and the Play internal track with no manual steps.

Estimated effort: 3–4 days plus review time

## Phase 10  ·  Post-Launch Operations

Objective: Keep it healthy.

Scope

- Weekly review of Sentry crash-free session rate; target above 99.5 percent.

- Monitor outbox failure rates — this is the metric that tells you whether data is being lost.

- Web content updates deploy continuously through Vercel; native binaries follow a monthly cadence unless something is broken.

- Track Apple and Google policy changes; both stores raise minimum SDK levels annually.

- Keep Capacitor and its plugins current; a year of drift makes the upgrade painful.

Exit gate: Operating rhythm established and documented.

Estimated effort: ongoing

# 9.  Timeline, Effort and Cost

| Week | Phases | Effort | Milestone |
| --- | --- | --- | --- |
| 1 | Phase 0, Phase 1 | 4–5 days | Buildable typed project, visually identical to today |
| 2 | Phase 2, Phase 3 | 5–6 days | Installable PWA with a proper mobile interface — first shippable value |
| 3 | Phase 4 | 4–5 days | Works offline; writes queue and replay reliably |
| 4 | Phase 5, Phase 6 (start) | 5 days | iOS and Android projects running on physical devices |
| 5 | Phase 6 (finish) | 4 days | Native capabilities complete; Risk R-1 closed |
| 6 | Phase 7, Phase 8 | 5 days | Compliance complete, quality gates green |
| 7 | Phase 9 | 3–4 days | First builds in TestFlight and the Play internal track |
| 8+ | Review and closed testing | calendar time | Apple review 1–7 days; Play closed test 14 days |

Total engineering effort: 25–30 focused working days. Calendar duration is longer, and the binding constraint at the end is store review time, not development.

## 9.1  Cost

| Item | Cost | Note |
| --- | --- | --- |
| Apple Developer Program | USD 99 / year | Mandatory for TestFlight and the App Store alike. |
| Google Play Developer | USD 25 one-time | Personal accounts carry the 12-tester closed-test requirement. |
| macOS build capability | Variable | An existing Mac is free. Otherwise GitHub Actions macOS minutes or Xcode Cloud. |
| Sentry | Free tier | Ample for a single-user or small-audience application. |
| Supabase, Vercel | Existing | No change. Storage growth from evidence photos is the only variable to watch. |
| Icon and store artwork | Optional | The existing "F" monogram and palette are strong enough to derive everything from. |

# 10.  Security and Privacy Posture

| Control | Implementation |
| --- | --- |
| Authentication | Supabase Auth, email and password. No third-party identity provider, so Sign in with Apple is not required. |
| Authorisation | Row Level Security remains the sole enforcement boundary. Phase 7 verifies this by attempting anonymous reads on all eleven relations. |
| Key handling | Publishable key only, injected at build time. No service-role key ever reaches the client bundle or the repository. |
| Session at rest | iOS Keychain and Android EncryptedSharedPreferences through the Capacitor Preferences adapter. Not localStorage. |
| Device access | Optional biometric application lock with a grace period. |
| Transport | HTTPS only. androidScheme set to https. Navigation restricted to the application origin; external links handed to the system browser. |
| Evidence files | Supabase Storage with signed URLs and RLS-governed access. No public buckets. |
| Telemetry | Sentry with personal data scrubbing enabled. No task content, no email addresses, no photographs. |
| Data subject rights | In-application export and irreversible deletion (Phase 7). |
| Isolation | No ATEMA data, credentials, infrastructure or documents at any point. This is an absolute constraint, restated in CLAUDE.md. |

# 11.  Submission Checklists

## 11.1  Apple App Store

| # | Item | Gate |
| --- | --- | --- |
| 1 | Apple Developer Program membership active | Phase 0 |
| 2 | Bundle identifier registered; APNs key created | Phase 5 |
| 3 | App icon 1024px, no alpha channel, no rounded corners | Phase 5 |
| 4 | Native capabilities implemented and demonstrable (Guideline 4.2) | Phase 6 |
| 5 | Info.plist usage strings for camera, photo library and Face ID | Phase 6 |
| 6 | In-app account deletion (Guideline 5.1.1 v) | Phase 7 |
| 7 | Privacy policy URL, publicly reachable | Phase 7 |
| 8 | App Privacy nutrition label completed from the field inventory | Phase 7 |
| 9 | Demo account credentials supplied in App Review notes | Phase 7 |
| 10 | Screenshots for 6.7-inch and 5.5-inch displays, Arabic | Phase 9 |
| 11 | Export compliance declaration (HTTPS only, exempt) | Phase 9 |
| 12 | Age rating questionnaire completed | Phase 9 |
| 13 | TestFlight build validated on a physical device before submission | Phase 9 |

## 11.2  Google Play

| # | Item | Gate |
| --- | --- | --- |
| 1 | Play Console account registered and identity verified | Phase 0 |
| 2 | Application signing enrolled; upload keystore backed up offline | Phase 9 |
| 3 | Target SDK meets the current Play requirement | Phase 5 |
| 4 | Data Safety form consistent with actual SDK behaviour | Phase 7 |
| 5 | Privacy policy URL in the store listing | Phase 7 |
| 6 | Account deletion available in-app and via a public web URL | Phase 7 |
| 7 | Content rating questionnaire completed | Phase 9 |
| 8 | Phone and tablet screenshots, feature graphic 1024 by 500 | Phase 9 |
| 9 | Closed test — 12 testers, 14 continuous days (personal accounts) | Phase 9 |
| 10 | Staged production rollout configured | Phase 9 |

# Appendix A  —  Agent Ticket Backlog

Hand these to Claude Code or Codex one at a time. The identical list is supplied as MOBILE_BUILD_PLAN.md for the agent to read directly from the repository — give the agent the markdown file, not this document.

### Rules for driving the agent

- One ticket per session. A session that touches two phases will quietly break the first one.

- The agent reads CLAUDE.md at the start of every session, without exception.

- No ticket is complete until its exit criteria are demonstrated, not asserted.

- Never permit schema changes, policy changes or migrations outside tickets M-24 and M-25.

- After each ticket: commit, push, and confirm the Vercel preview deployment still works.

| ID | Title | Exit criteria |
| --- | --- | --- |
| M-01 | Tag baseline and capture reference screenshots | Tag v0-web-baseline pushed; five views captured at 390/768/1440px under docs/baseline/ |
| M-02 | Author CLAUDE.md guardrails | File committed at repository root, content matching Appendix C |
| M-03 | Scaffold Vite + TypeScript, strict mode | npm run build produces dist/; tsc --noEmit clean |
| M-04 | Extract CSS tokens and split stylesheets | No computed style differs from the M-01 screenshots |
| M-05 | Split JavaScript into app/ and features/ modules | All five views function identically; no behavioural change |
| M-06 | Bundle Supabase; move config to VITE_ env vars | No CDN request at runtime; .env.example committed; .env ignored |
| M-07 | Generate typed row models from the live schema | src/app/types.ts covers all eleven relations |
| M-08 | Introduce typed repositories per table | No supabase.from() call remains inside any feature module |
| M-09 | Configure Vercel build; verify the production domain | Preview and production deployments succeed unchanged |
| M-10 | Add vite-plugin-pwa, manifest and icon set | Installable on iOS Safari and Android Chrome |
| M-11 | Workbox caching strategies and offline shell | Network disabled: designed offline state, not a browser error |
| M-12 | Service worker update prompt (Arabic) | New build offers an update instead of reloading beneath the user |
| M-13 | Responsive shell — bottom tabs below 900px | Five tabs; sidebar preserved at desktop widths |
| M-14 | Safe-area insets and 44pt minimum touch targets | Nothing under notch or home indicator; audit shows no target below 44pt |
| M-15 | RTL verification and skeleton loading states | Tab order, mirroring and LTR inputs all correct |
| M-16 | Pull-to-refresh on Today and Projects | Gesture refreshes and reconciles without a full reload |
| M-17 | IndexedDB read cache with reconciliation | Views render from cache instantly on a cold start |
| M-18 | Write outbox with idempotency and replay | Aeroplane-mode writes land exactly once on reconnect |
| M-19 | Conflict policy and pending-sync indicator | Completed tasks never revert; pending count visible in the header |
| M-20 | Capacitor init; add iOS and Android projects | Both build and launch on physical devices |
| M-21 | Icons, splash, status bar, edge-to-edge | Brand-correct launch experience on both platforms |
| M-22 | Android back button and deep-link handling | Back navigates the router; links resolve to the right view |
| M-23 | Secure session storage adapter | Session survives app restart and OS storage eviction |
| M-24 | Push notifications (client + Edge Function) | Test notification received on both platforms; app fully usable if denied |
| M-25 | Camera evidence capture with web fallback | Photo reaches Supabase Storage against task_evidence; file input on web |
| M-26 | Biometric app lock with passcode fallback | Opt-in, grace period honoured, fallback works |
| M-27 | Native share and haptics | Share sheet opens with correct content; haptics on completion |
| M-28 | iOS usage strings and Android runtime permissions | All strings present in Arabic and English; rationale shown in context |
| M-29 | Account deletion (UI + Edge Function) | Auth user and all owned rows removed; irreversible; confirmed |
| M-30 | Data export to JSON | Valid file containing every record the user owns |
| M-31 | Privacy policy, terms, and the field inventory | URLs live; inventory table complete and accurate |
| M-32 | Anonymous access verification on all relations | Zero rows returned without a JWT on every one of the eleven relations |
| M-33 | Playwright end-to-end suite | Auth, five views, offline and outbox all covered and green |
| M-34 | Vitest unit coverage on outbox, cache, repositories | Coverage above 80 percent on those three modules |
| M-35 | Lighthouse thresholds enforced in CI | Performance 90+, Accessibility 95+, PWA passing |
| M-36 | Sentry with release tagging and source maps | A deliberate test error appears correctly symbolicated |
| M-37 | GitHub Actions ci.yml | Runs on every pull request; blocks merge on failure |
| M-38 | release-android.yml — signed .aab to internal track | Unattended upload succeeds from a tag |
| M-39 | release-ios.yml — .ipa to TestFlight | Unattended upload succeeds from a tag |
| M-40 | Store listings, screenshots and review notes | Arabic and English listings complete; demo credentials included |

# Appendix B  —  Reference Configuration

Starting points, not finished files. The agent adapts them; it does not invent alternatives to them.

### B.1  capacitor.config.ts

import type { CapacitorConfig } from '@capacitor/cli';

const config: CapacitorConfig = {

appId: 'com.farajaay.fatimahworkos',

appName: 'Fatimah Work OS',

webDir: 'dist',

android: { adjustMarginsForEdgeToEdge: 'auto' },

ios: { contentInset: 'always', limitsNavigationsToAppBoundDomains: true },

server: { androidScheme: 'https' },

plugins: {

SplashScreen: { launchAutoHide: false, backgroundColor: '#fbf7f2' },

StatusBar:    { style: 'LIGHT', backgroundColor: '#fbf7f2' },

PushNotifications: { presentationOptions: ['badge', 'sound', 'alert'] }

}

};

export default config;

### B.2  Supabase auth storage adapter (fixes silent logout on iOS)

// src/data/session-storage.ts

import { Preferences } from '@capacitor/preferences';

import { isNative } from '../platform/capabilities';

export const secureStorage = {

async getItem(key: string) {

if (!isNative()) return localStorage.getItem(key);

return (await Preferences.get({ key })).value;

},

async setItem(key: string, value: string) {

if (!isNative()) { localStorage.setItem(key, value); return; }

await Preferences.set({ key, value });

},

async removeItem(key: string) {

if (!isNative()) { localStorage.removeItem(key); return; }

await Preferences.remove({ key });

}

};

// src/data/supabase.ts

export const supabase = createClient(

import.meta.env.VITE_SUPABASE_URL,

import.meta.env.VITE_SUPABASE_ANON_KEY,

{ auth: { storage: secureStorage, persistSession: true, autoRefreshToken: true } }

);

### B.3  Outbox contract

type OutboxEntry = {

id: string;              // uuid v4 — also the idempotency key

table: 'tasks' | 'achievements' | 'events' | 'workflow_runs';

op: 'insert' | 'update' | 'delete';

payload: Record<string, unknown>;

createdAt: number;

attempts: number;        // give up and surface to the user after 5

};

// Replay rules

// 1. FIFO by createdAt.

// 2. On conflict, last write wins on updated_at —

//    EXCEPT task completion, which is monotonic and never reverts.

// 3. Never queue auth operations or evidence deletions; fail loudly instead.

// 4. Surface pending count in the header at all times.

### B.4  package.json scripts

"scripts": {

"dev":        "vite",

"build":      "tsc --noEmit && vite build",

"preview":    "vite preview",

"test":       "vitest run",

"test:e2e":   "playwright test",

"lint":       "eslint src --max-warnings 0",

"sync":       "npm run build && npx cap sync",

"ios":        "npm run sync && npx cap open ios",

"android":    "npm run sync && npx cap open android",

"assets":     "npx @capacitor/assets generate --iconBackgroundColor '#fbf7f2'"

}

### B.5  Android release workflow (abridged)

name: release-android

on: { push: { tags: ['v*'] } }

jobs:

build:

runs-on: ubuntu-latest

steps:

- uses: actions/checkout@v4

- uses: actions/setup-node@v4

with: { node-version: '20', cache: 'npm' }

- run: npm ci && npm run build && npx cap sync android

- uses: actions/setup-java@v4

with: { distribution: 'temurin', java-version: '21' }

- run: ./gradlew bundleRelease

working-directory: android

env:

KEYSTORE_B64:     ${{ secrets.ANDROID_KEYSTORE_B64 }}

KEYSTORE_PASS:    ${{ secrets.ANDROID_KEYSTORE_PASS }}

- uses: r0adkll/upload-google-play@v1

with:

serviceAccountJsonPlainText: ${{ secrets.PLAY_SERVICE_ACCOUNT }}

packageName: com.farajaay.fatimahworkos

releaseFiles: android/app/build/outputs/bundle/release/app-release.aab

track: internal

# Appendix C  —  CLAUDE.md Guardrails

Committed to the repository root. The agent reads it at the start of every session. Supplied as a separate file alongside this document.

# Fatimah Work OS — Agent Guardrails

## Never

- Never change the Supabase schema, RLS policies or existing migrations,

except in tickets M-24, M-25 and M-29, and then only additively.

- Never add a service-role key, database password, OpenAI key or any other

secret to the repository. Publishable client key only, via env vars.

- Never touch, reference or import ATEMA data, credentials or infrastructure.

- Never redesign the visual language. Colours, typography and layout tokens

come from the original index.html and are preserved exactly.

- Never rewrite the app in React, Vue, Flutter or React Native.

- Never work on more than one ticket in a session.

## Always

- Read this file first, every session.

- Confirm the ticket ID and its exit criteria before writing any code.

- Keep the interface Arabic and RTL. Latin-script inputs stay LTR.

- Run: npm run build && npm run lint && npm test before declaring done.

- Compare against docs/baseline/ screenshots after any UI-adjacent change.

- Keep the web build working. It is a shipping product, not scaffolding.

- Commit per ticket with the ticket ID in the message: "M-14: safe-area insets".

## Definition of done

A ticket is done when its exit criteria are DEMONSTRATED — a screenshot,

a passing test, or a device recording. Not when the code looks correct.

# Appendix D  —  Acceptance Test Matrix

| Area | Test | Pass condition |
| --- | --- | --- |
| Parity | All five views against the Phase 0 screenshots | No visual regression at 390, 768 and 1440px |
| Authentication | Login, signup, logout, session restore after force-quit | Session survives restart; no silent logout |
| Offline read | Aeroplane mode, cold start | All five views render cached data within 3 seconds |
| Offline write | Create and complete tasks with no network, then reconnect | Every change lands exactly once; no duplicates |
| Conflict | Complete a task offline while it is also updated on the server | Completion is preserved; it does not revert |
| Push | Send a test notification to both platforms | Delivered and deep-links to the correct view |
| Push denied | Deny notification permission, then use the whole app | No feature blocked, no nagging prompt |
| Camera | Capture task evidence on device and on web | Uploaded to Storage; visible against the task |
| Biometric | Enable lock, background the app past the grace period | Prompt appears; passcode fallback works |
| Deletion | Delete the account from Settings | Auth user and all owned rows gone; login fails afterwards |
| Security | Anonymous REST call against all eleven relations | Zero rows on every one |
| Accessibility | VoiceOver and TalkBack in Arabic; 200 percent type | Full navigation; no clipping or overlap |
| Performance | Cold start on the slowest device in the matrix | Interactive in under 3 seconds |
| Back button | Android hardware back across all views | Navigates the router; exits only from a root tab |

# Document Control

| Rev | Date | Author | Change |
| --- | --- | --- | --- |
| 0 | 26 Aug 2026 | Prepared for A. AlFaraj | Issued for execution. Baseline established from the repository snapshot dated 25 Aug 2026. |
|  |  |  | Open item: Phase 0 audience decision (Risk R-3) to be recorded here before Phase 7 begins. |